## Cover Page
SMART SHOP
Sprint Backlog
|  | Prepared By / Last Updated By | Reviewed By | Approved By
| Name | Vijayadithya Doddi
| Role | Developer
| Signature | VD
| Date | 2019-11-29
Project ID: Car Servicing | HYD19IJ001 |  |  | <SCI.ID> / Ver: <No.>
C3: Protected
:
Controlled copy
Controlled copy
Controlled copy
Controlled Copy

## Instructions
Sprint Backlog <Instructions> Project ID: <Batch code/project id> C3: Protected Controlled Copy
Sprint 1/2
The Sprint sheets has to be filled for each sprint
The Sprint Backlog is the set of Product Backlog items selected for the Sprint, plus a plan for delivering the product Increment and realizing the Sprint Goal. The Sprint Backlog is a forecast by the Development Team about what functionality will be in the next Increment and the work needed to deliver that functionality into a “Done” Increment.The Sprint Backlog is the output of the sprint planning meeting. It is essentially the list of tasks that the Scrum team needs to complete during the sprint in order to turn a selected set of product backlog items into a deliverable increment of functionality.
| Feature Id | List the feature id taken from product backlog that are selected to be completed in the particular sprint.
| Task No | List the number tasks the feature is split into.
| Task | Name the tasks the feature is split into.
| Owner | Name the person responsible for the particular task
| Status | Status of the Task - In progress/Completed
| Original Estimate | Original estimate of the task
| Day 1/2/3/4/5/6 | Task done in Day1/2/3/4/5/6 - Sprint review and retrospective to be held on Day 6
| Total | Summation of the estimation of the per day. To be filled with the total of the estimations filled.
| Charts | Chart is self driven as per the task burned

## Sprint 1
Sprint Backlog Smart Shop Project ID: HYD19IJ001 C3: Protected Controlled Copy
Feature Id | Task No | Task | Owner | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Status
Req_1 | Req_1.1 | When the user clicks on the registration link, it should re-direct to registration form. | Vijayadithya Doddi | 0.15 | 1 | NA | NA | 1 | NA | NA | Completed
Req_1 | Req_1.2 | User needs to fill some of the basic attributes/fields as mentioned below in requirement: First Name, Last Name, Age, Gender, Contact Number, User Id, Password | Vijayadithya Doddi | 0.15 | 1 | NA | NA | 1 | NA | NA | Completed
Req_1 | Req_1.3 | Clicking ‘Submit’ should validate the datatype constraints for each field | Vijayadithya Doddi | 0.15 | 1 | NA | NA | 1 | NA | NA | Completed
Req_1 | Req_1.4 | User failing to provide information on the mandatory fields be provided with an alert message – ‘Please update the highlighted mandatory field(s).’ Also, highlight the missed out field in red | Vijayadithya Doddi | 0.15 | 1 | NA | NA | 1 | NA | NA | Completed
Req_1 | Req_1.5 | Post-successful field level validation, save the information in the database | Vijayadithya Doddi | 0.15 | 1 | NA | NA | 1 | NA | NA | Completed
Req_1 | Req_1.6 | Upon saving the information in the database, display the message ‘Your details are submitted successfully’. | Vijayadithya Doddi | 0.15 | 1 | NA | NA | NA | 1 | NA | Completed
Req_2 | Req_2.1 | A registered user – is able to click ‘Login’ link, after keying in ‘User ID’ & ‘Password’ field and get his credentials authenticated with the existing database entry | Vijayadithya Doddi | 0.15 | 1 | NA | NA | NA | 1 | NA | Completed
Req_2 | Req_2.2 | A registered user – is unable to login and get the credentials authenticated, the user is presented with relevant error messages:Invalid User ID (or) Incorrect Password | Vijayadithya Doddi | 0.15 | 1 | NA | NA | NA | 1 | NA | Completed
Req_3 | Req_3.1 | On successful login of the user account, user should be able to search for products available in the stock. | Vijayadithya Doddi | 0.15 | NA | NA | 1 | NA | 1 | NA | Completed
Req_3 | Req_3.2 | Ability of the portal to allow the user to sort the displayed items with below sort options: Sort by Name Sort by Popularity Sort by Availability Sort by Price | Vijayadithya Doddi | 0.15 | NA | NA | 1 | NA | 1 | NA | Completed
Req_3 | Req_3.3 | On selecting the required product, system to display the exact location of the product to ease the customer in picking it. | Vijayadithya Doddi | 0.15 | NA | NA | 1 | NA | 1 | NA | Completed
Req_4 | Req_4.1 | Portal to allow the Admin to create user accounts with Shop Manager privileges | Vijayadithya Doddi | 0.15 | NA | 1 | NA | NA | NA | 1 | Completed
Req_4 | Req_4.2 | Admin needs to fill some of the basic attributes/fields as mentioned below in requirement to create new admin profile: First Name, Last Name, Age, Gender, Contact Number, User Id, Password | Vijayadithya Doddi | 0.15 | NA | 1 | NA | NA | NA | 1 | Completed
Req_4 | Req_4.3 | Clicking ‘Submit’ should validate the datatype constraints for each field | Vijayadithya Doddi | 0.15 | NA | 1 | NA | NA | NA | 1 | Completed
Req_4 | Req_4.4 | Provide failing to provide information on the mandatory fields with an alert message – ‘Please update the highlighted mandatory field(s).’ Also, highlight the missed out field in red | Vijayadithya Doddi | 0.15 | NA | 1 | NA | NA | NA | 1 | Completed
Req_4 | Req_4.5 | Post-successful field level validation, save the information in the database | Vijayadithya Doddi | 0.15 | NA | 1 | NA | NA | NA | 1 | Completed
Req_4 | Req_4.6 | Upon saving the information in the database, display the message ‘Your details are submitted successfully’. | Vijayadithya Doddi | 0.15 | NA | 1 | NA | NA | NA | 1 | Completed
Req_4 | Req_4.7 | Shop manager registration will need approval from Super user | Vijayadithya Doddi | 0.15 | NA | NA | 1 | NA | NA | 1 | Completed
Req_4 | Req_4.8 | Super User should have a page to display all the registration request for Shop manager | Vijayadithya Doddi | 0.15 | NA | NA | 1 | NA | NA | 1 | Completed
Req_4 | Req_4.9 | Super user can approve or deny the request | Vijayadithya Doddi | 0.15 | NA | NA | 1 | 1 | NA | NA | Completed
Req_4 | Req_4.10 | Upon approval, Shop manager should be able to login. If denied, it should display error message “Registration not approved.” | Vijayadithya Doddi | 0.15 | NA | NA | 1 | 1 | NA | NA | Completed
Req_19 | Req_19 | When the user clicks Log off, the system should disconnect from the system. | Vijayadithya Doddi | 0.15 | NA | 1 | NA | 1 | NA | NA | Completed
[5 empty] | NA | 1 | NA | 1 | NA | NA
|  | Total |  | 3.3 | 8 | 8 | 7 | 9 | 6 | 8
Sprint Goal
Some sprint goal

## Sprint 2
Sprint Backlog Smart Shop Project ID: HYD19IJ001 C3: Protected Controlled Copy
Feature Id | Task No | Task | Owner | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Status
Req_5 | Req_5.1 | A registered Shop manager – is able to click ‘Login’ link, after keying in ‘User ID’ & ‘Password’ field and get his credentials authenticated with the existing database entry. | Vijayadithya Doddi | 0.15 | 1 | NA | NA | 1 | NA | NA | Completed
Req_5 | Req_5.2 | A registered Shop manager – is unable to login and get the credentials authenticated, the user is presented with relevant error messages: | Vijayadithya Doddi | 0.15 | 1 | NA | NA | 1 | NA | NA | Completed
Req_6 | Req_6.1 | Invalid User ID (or) IncorrectWhen the shop manager Logs in with valid details he should be allowed to add/modify/delete or update the products in the inventory. Password | Vijayadithya Doddi | 0.15 | 1 | NA | NA | 1 | NA | NA | Completed
Req_6 | Req_6.2 | Shop manager needs to fill the basic details of the product like product name, product image, number of items available, date of manufacturing date and date of expiry | Vijayadithya Doddi | 0.15 | 1 | NA | NA | 1 | NA | NA | Completed
Req_6 | Req_6.3 | Clicking ‘Submit’ should validate the datatype constraints for each field and update the stock | Vijayadithya Doddi | 0.15 | 1 | NA | NA | 1 | NA | NA | Completed
Req_7 | Req_7.1 | Shop manager on clicking Add Product, it should redirect to the Product Addition page | Vijayadithya Doddi | 0.15 | 1 | NA | NA | NA | 1 | NA | Completed
Req_7 | Req_7.2 | Shop Manager needs to fill some of the basic attributes/fields as mentioned below in requirement to create new Product: Product ID, Product Name, Brand, Type, Quantity type, Rate per Quantity, Stock Count | Vijayadithya Doddi | 0.15 | 1 | NA | NA | NA | 1 | NA | Completed
Req_7 | Req_7.3 | Clicking ‘Submit’ should validate the datatype constraints for each field | Vijayadithya Doddi | 0.15 | 1 | NA | NA | NA | 1 | NA | Completed
Req_7 | Req_7.4 | Provide failing to provide information on the mandatory fields with an alert message – ‘Please update the highlighted mandatory field(s).’ Also, highlight the missed out field in red | Vijayadithya Doddi | 0.15 | NA | NA | 1 | NA | 1 | NA | Completed
Req_7 | Req_7.5 | Post-successful field level validation, save the information in the database | Vijayadithya Doddi | 0.15 | NA | NA | 1 | NA | 1 | NA | Completed
Req_7 | Req_7.6 | Upon saving the information in the database, display the message, ‘Your details are submitted successfully’. | Vijayadithya Doddi | 0.15 | NA | NA | 1 | NA | 1 | NA | Completed
Req_8 | Req_8.1 | Shop manager on clicking billing, should redirect to the billing page | Vijayadithya Doddi | 0.15 | NA | 1 | NA | NA | NA | 1 | Completed
Req_8 | Req_8.2 | On selecting the product type, the system should list the available items for that type | Vijayadithya Doddi | 0.15 | NA | 1 | NA | NA | NA | 1 | Completed
Req_8 | Req_8.3 | On selecting the item it should populate the rate and shop manager can enter the quantity | Vijayadithya Doddi | 0.15 | NA | 1 | NA | NA | NA | 1 | Completed
Req_8 | Req_8.4 | Option should be there for the shop Manager to enter the product code for billing | Vijayadithya Doddi | 0.15 | NA | 1 | NA | NA | NA | 1 | Completed
Req_8 | Req_8.5 | After entering all the items, system should sum up and display the total amount. The shop manager should update the customer phone number and tag the purchase to the customer. | Vijayadithya Doddi | 0.15 | NA | 1 | NA | NA | NA | 1 | Completed
Req_8 | Req_8.6 | Shop manager should complete the billing by clicking submit. | Vijayadithya Doddi | 0.15 | NA | 1 | NA | NA | NA | 1 | Completed
Req_9 | Req_9.1 | The system should deduct the count of the quantity billed from the total stock once billing is done. | Vijayadithya Doddi | 0.15 | NA | NA | 1 | NA | NA | 1 | Completed
Req_10 | Req_10.1 | Shop manager on clicking submit in Billing, should update the purchase history of the customer in the database | Vijayadithya Doddi | 0.15 | NA | NA | 1 | NA | NA | 1 | Completed
Req_11.1 | Req_11 | Shop manager on clicking Update Aisle / Shelf details, should display the product types available | Vijayadithya Doddi | 0.15 | NA | NA | 1 | 1 | NA | NA | Completed
Req_11.2 | Req_11 | Shop manager on clicking a product type, should display all the product under that type | Vijayadithya Doddi | 0.15 | NA | NA | 1 | 1 | NA | NA | Completed
Req_11.3 | Req_11 | Shop manager on clicking the Product code, should allow him to update the aisle and shelf details | Vijayadithya Doddi | 0.15 | NA | 1 | NA | 1 | NA | NA | Completed
Req_11.4 | Req_11 | On clicking Submit, should update the details in the DB. The system should have necessary validations for the required fields | Vijayadithya Doddi | 0.15 | NA | 1 | NA | 1 | NA | NA | Completed
|  | Total |  | 3.45 | 8 | 8 | 7 | 9 | 6 | 8
Sprint Goal
Some sprint goal

## Data (hidden)
In-Progress
Completed
N/A